## Slide 1: Proposal for the Ticketing development project
Take One Movie Theatre

## Slide 2: Table of content
Background
Problem Statement
Constraints
Scope Definition
Goals of project
Opportunities to improve
Schedule
Budget
Internal Resources

## Slide 3: 1. Background
The TAKE ONE movie theatre is a new up and coming movie theatre in a residential area of South Africa. The movie theatre will show recently released movies as well as special movies for special occasions (e.g. Christmas season, Valentine’s day, ladies’ night). Audience members will be able to book tickets for the movie of their choice. Each day there will be a specific time schedule according to which the movies will be shown. Members (loyalty program) of the movie theatre will receive special deals and newsletters.
There is currently no automated system in place at the movie theatre, and the owners requested a system that is not run by a third party. However we will implement an Information System using existing hardware.

## Slide 4: 2. Problem Statement
There is no automated system in place at the theatre to satisfy the owners’ business requirements.
The following important business processes needs to be automated:
  Seat booking system (Notification system)
  Specify which movies that is shown in the theatre.
Reporting must be implemented e.g. popular movie genre attended per year, most frequent nights visited, profit margins.

## Slide 5: 2. Problem Statement Continued
The current system in place is a simple point of sale system that incorporated no automation. The tickets must be bought at the movie theatre. This can cause clients to arrive at the movie theatre but there is no space available in the movie theatre.
Help function is needed for new users and clients using the system.
There is no transaction history to predict what time shows are most popular.
The system should allow clients to book seats for shows over the internet.

## Slide 6: 3. Constraints
There is currently no automated system in place at the theatre. The necessary hardware to run the system is already in place at the movie theatre.
Budget of only R 300 000.
All the necessary licences to develop the project, we as a company own. The movie theatre does not need any special software to run the system other than the Windows operating system which is already in place.
The system must be fully functional and implemented by November 2020 before the festive season starts.

## Slide 7: 4. Scope Definition
The system must include functionality for the following:
Maintain clients of movie theatre
Maintain movies
  Regular movies that are newly released
  Special occasions (Valentines, ladies & boys nights, etc.)
Selling of tickets
  Notify client about ticket information when sale is complete.
  The notification will include their movie ticket code.
Indicate seats that are booked.

## Slide 8: 4. Scope Definition Continued
Export data
  Backups
  Profit margins
Request report:
  List of movies
  Attendance list of movies to determine popular genre per time period (e.g. comedy, drama, action)
  Audience size per time period (time of day, day of weekend)
  Graphical representation of popular times movies are watched.

## Slide 9: 5. Goals of project
The following goals were identified for the system:
The system must improve the business knowledge by:
  Providing reports of movies that was well received by the audience. The reports must clearly state which genre of movies is most popular.
  Informing the clients of which shows are in high-demand.

## Slide 10: 5.Goals of project Continued
The system must improve the business processes by:
  Automating ticket sales. The ticket sales must be done over the internet.
  Reserving seats that are already booked to ensure that no double bookings occur.
The system must improve the business communication by:
  Providing a graphical user interface that supports a common language to accommodate most clients.
  Notifying the client when their seat/s have been successfully booked by sending their ticket code via e-mail.

## Slide 11: 6. Opportunities to improve
The following opportunities to improve were identified:
  Additional WhatsApp system to confirm the booking and send the e-ticket to. WhatsApp is more accessible to more users in today’s day and age.
  Multiple language interface to accommodate more clients. This must ask the user of their preferred language. The system will continue in the selected language.
  If the theatre has the opportunity to expand, theatres must be maintained. The possibility for the new theatre to expand must be taken into consideration for the future.
  QR code scanners can be implemented to ease the checking of tickets at the movie theatre. This will show the movie the client will watch and which seats are booked.

## Slide 12: 7. Schedule
Project Steps | Steps Implemented | Proposed date
Scope definition | Scope definition documented in the project proposal. | 24-02-2020
Problem analysis | The project proposal with the existing problems, proposed solutions to the problems, business opportunities, schedule of events and the economic justification. | 24-02-2020
Requirements analysis | Business requirement statements | 20-03-2020
Logical design | Specifications and the logical system modules | 04-05-2020
Decision analysis | Document with evaluation for each candidate solution in terms of technical-, operational-, economic-, schedule- and risk- feasibility Choose best candidate solution and decide whether project must be completed | 04-05-2020
Physical design & integration | Physical design models Detail specifications Prototypes Redesigned business processes | 07-08-2020
Construction & testing | Database Custom-built software User Interfaces (Windows or Web) Test plan | 04-09-2020
Installation | An operational system Operation manual Documented quality review Updated logical and physical system models | 02-10-2020

## Slide 13: 8. Budget
Man-hour cost:
Cost from Scope definition till Decision analysis
= 5 people working 5 hours a week and working for 8 weeks @ R450/h
= 5 x 5 x 8 x 450
= R 90 000
Cost from Physical design and integration
= 5 people working 10 hours a week and working for 8 weeks @ R450/h
= 5 x 10 x 8 x 450
= R 180 000

## Slide 14: 8. Budget continued
Software cost:
None: Assumption was made that the hardware currently running at the theatre has Windows installed that is needed for the system to fully function. Currently no other software requirements are needed.
Recurring cost:
Website host: R 69/month from Domains.co.za for 12 months
5GB bandwidth
25 email accounts
1 website
5 MySQL databases
Total project cost: R 270 828

## Slide 15: 9. Internal Resources
The internal resources for the project are:
System owner (sponsor):
  Director Charlotte Doyle
System user (client-based):
  Clients buying tickets using the system.
System user (employee-based):
  Jamie Hansen (manager)
  Arthur Finn
  Tom Adler

## Slide 16: 9. Internal Resources Continued
The following system will be developed by
Johané le Roux
Christopher Slaghuis
Jean Marx
Reinhardt Nel
James Uys